## Input Tool
Priority | Item Number (IT- #) | Item | Description | Contact Name | Group approved | Resolved (Yes or No/Date) | Comments
1 | IT-4 | Changing the date of a datasheet | We need to be able to change the date on the “datasheet” after you have started entering data without having to click F2. Remove the F2 function so it's easier to change date | Lauren | Yes | In progress | If you remove the F2 function and change the date, it won't change the date it will create a new datasheet for that subsector.The only way around this (compromise) is to add a change date button (next to the date)instead of having to press F2.
1 | IT-6 | Pop up when changing sent/accepted sheet | When changing or adding a duplicate with the F-functions on a sheet that is in sent or accepted mode, there is no pop up alerting the user to resend the data | Julie | yes
1 | IT-10 | R-log calculation error | It has been noticed that ‘sometimes’ the R-log daily duplicate value is not calculated correctly. For example, MPN duplicate combo of 1.9 and 2.0, R log is calculated as 0.30103 within the input tool but it should be 0.0223. | NL | yes
1 | IT-11 | Calendar is inconvenient. | When entering data for a run conducted in a previous month, you can only go back a single month at a time and the drop down closes. This is not great when entering May data, say in October. If calendar can not be changed, SOP should be updated to include calendar selection process described by Charles in the email. | NL | Yes | N/A | Charles: Put explenation in SOP
1 | IT-13 | "Processed by" field for daily duplicates | All data self populates based on the original sample with the exception of FC data (which shouldn’t) and processed by initials (which should). This is a potential source of error that can easily happen. | NL | yes | In progress | The processed by column works differently then the others. Remember we wanted a dragged down option (like excel) but this wasn't possible so Charles modified the rules for this column so that it would take the initials of the cell above it. This can cause errors for daily dups, intertech and reading dup so we removed for those 3 that rule. This means however that we have to input the tech initials for those 3 dups moving forward
1 | IT-14 | Updating of daily duplicate info | Daily duplicate info doesn’t update if original sample data is changed which gives us an opening for error. For example, if you go back and change the salinity in the original, the duplicate info will not update unless you do so manually. | NL/NS | yes
1 | IT-15 | TC First/Average | What is this? It appears to be referring to/calculating salinity in the input tool, not temperature. REMOVE FIRST AND AVERAGE, not a necessity and space could be used for water bath info. Charles you can use the space saved here to move the bath one info from the full version down bellow the field lab temps. | NL | yes
1 | IT-17 | cells change blue for changes | do we need the cells to change blue if changes are during the initial data entry. I thought it was only after it was sent and changes were made that they turned blue. Changes revelance is being lost. Could it only track changes once you leave a sheet and come back to it? | NS | yes
1 | IT -19 | "send to server" | When you enter your data and hit "send to server" it takes you to another page with detail logs and programming details. Can it be a quick box with "are you sure you want to send to server?" on the same page as the data entry rather than take you to separate page. If not the separate page should highligh the send button .. why is there a "send to server" button if it doesnt do anything. Or the pop up box could also ask if you want to see the changes or details. | NS | yes |  | This sheet is there at our request. This step is between sending it and overwritting something by accident. We need to check this screen before sending but it most cases, there will be no differences so the extra screen will not show up. He will put the cancel and send button in color so that we see it easier.
1 | IT-20 | data entry page drop down beside date | identify what the drop down from 1-20 is … runs? Students have mistaken this for sampling day and other could think of using this as run 1 of 5 instead of it's intended use. Could we add some text next to it (multiple runs same day) or in the help button? | NS | yes
1 | IT-21 | negative temperatures | negatives can be entered but show as red, asked if you want to accept and when you do it shows site- type in RED but removes the negative temperatures and no email is sent for approval. NB also: Contractors reported not being able to put (minus) temperatures in the input tool. I tried also and we can't (put's it in red) . This was ITEM WT 6 before. Moved to this list | NS/NB | yes
2 | IT-2 | Error in log record (light version) | In the light version of input tool, the log shows that two coolers were used. There is no option for multiple coolers so this should just be left out of the contractor version. | Lauren | Yes
2 | IT-5 | Tides | My contractors may not have internet access all the time so they may have to manually type in the tide cycle. Please add an example of the correct tide cycle format beside the tide entry field. Either put it directly next to box or in a help button | Lauren | Yes |  | I you press F1 anywhere, it gives more info in the bar at the bottom. There is the allowable list of tides but will add an example. Also, tides can be inputed later when there is a connection.
2 | IT-9 | Auto Tab | The auto tabbing feature (for full version) needs to be consistent. The flow is not great when some fields auto tab and others don’t. We thought we would get used to it but never did. We recommend that the auto tab feature for bath incubation times and control results be removed. | NL | yes
3 | IT-1 | Add drop down option for duplicates (light version of input tool) | Hold of on this item-more discussion about how to handle duplicate data...We need to have a drop down option for adding an intertech duplicate sample or changing the duplicate number. Hitting F2 and F3 is not user friendly, we want an obvious visual button to click on. | Lauren | Yes-NS to expand |  | Charles will (instead of having to press F1 for the help), will auto populate the helpful info in the status bar bellow. SO when selecting the station number, it will is your options bellow. Will look into other option if possible.
3 | IT-3 | Emails | When a datasheet is edited/changed, after being previously sent to the web tool, and you re-upload/re-send it, the auto generated email should say “revised or modified lab sheet sent” instead of “new” | Lauren | Yes
3 | IT-7 | Highlighting Site-Type column when working in a row | We think that it would useful if the Site-Type column could become ‘highlighted’ when working in any cell within the row because it is difficult to see what site you are working with when, for example, entering data in comments field. This would be useful for data entry QC process as well. | NL | yes
3 | IT-12 | Placement of bath incubation times | When using multiple baths, why are bath 1 and 2 incubation times in different areas? Bath 2 incubation time should be moved over underneath Bath 1. Brain strom on reorginasing things if possible espicially concidering more space will be available due to IT-15 | NL | yes |  | I think this was addressed - it’s a real estate issue. GP. Charles will correct this with a new option since now we are removing the TC average and First TC.
3 | IT 22 | interface layout - main page | label of the drop down menus and create some separation between creating new sheets and searching existing sheets. (in the archive section, there is room to add some text) | NS | yes
No action needed | IT-8 | Mandatory entry of site sampling time. | While sampling time should always be recorded in the field, we had an occasion this summer where a student forgot to record this data. This created a challenge for data entry. To make it work, we had to estimate sample times. Hopefully this never happens again but it is always possible. Thoughts on how to deal with this? Suggest estimating time and noting it in the comments?? PD. Write this in the Data entry SOP | NL | yes | N/A | Added this to the document review excell for 2018

## Web Tool
Priority | Item Number (ex. WT- #) | Item | Description | Contact Name | Group approved | Resolved/ Date (Yes or No) | Comments
1 | WT-4 | Error message when accepting a datasheet | Error message when trying to accept a previously accepted datasheet. Same date just different sample data. Possible cause was a change in the list of stations-we added two stations in between accepting the first datasheet and the second acceptance. | Lauren | yes | Was not able to recreate error | I will need to do more test on this. But for now I can't reproduce the error. (Charles)
1 | WT-12 | Summary Statisics table | Can we add buttons to hide columns (i.e Max Fc, Colour coded class) | Pre-Arisc fall 2017 | yes | Yes | Need group discussion. Is this on CSSPWebTools or just the reports outputs (Charles)
1 | WT-13 | FC Data table | When you remove a run (removed from statistics) can you hide it in the table, it is still showing currently) | Pre-Arisc fall 2017 | yes | Yes… maybe (see WT-31) | This one will depends on the way we will show raw data in the reports (need group discussion). If the group still wants this to be the case it can be done…
1 | WT-15 | Stats | In the stats page (pile of wood), if you click to show temperature or salinity it would be nice to have a 'T' and an 'S' beside value | Patrice | yes | yes
1 | WT-16 | Stats table -report | In the full report on at the bottom of the Summary stats table you see the end date as 1985, should be last year in stats. | Pre-Arisc fall 2017 | yes | Yes
1 | WT-17 | Stats (same as WT-12) | Ability to hide the 260 (not used in NFLD) | Dave Curtis | yes | Yes | * And possibly other fields as well. Nice to have some user configurability options. I believe that NS also omits MAX FC (GP) see WT-12 (Charles)
1 | WT-19 | sample type drop down | selected or defaulted sample type should show on the top of the drop downlist. Can the one selected be bumped to the top. Also remove duplicate, intertech read/ intertech duplicate from this drop down list. This is actually "run type" | PD | yes | Yes
1 | WT-22 | ASGAD Precip | Need to be able to select "ASGAD" as a precip source on the Climate sites tab | Greg | yes | Later
1 | IT-16 | File summary bubble (ie sample plan) | Grey total number of files being tracked is not reflected in the bubble | NS | yes | Later | These gray bubbles are recalculated once in a while for now because we are still importing a lot of data from ASGAD and others. Later all these bubbles will be calculated automatically. It's already in the system, I just removed it temporarily.
1 | WT-26 | duplicate comment on the webtool needs to be changed | The comment "Where duplicate results differ in value, the highest value will serve as the daily result and the lower value as duplicate result for QA/QC purposes." Recommended change would be "Where duplicate results differ in value, the higher result will be used in data computation." | NS | yes | yes
2 | WT-5 | Sampling plan | Can the MPN, water and lab selection be done in the sampling plan first so it shows up by default but still have the option to change it at the acceptance stage? (you only have to select it once per subsector at the moment but when you have a new sampling plan, you have to do it again) Agreed! | Julie/ NS | yes
2 | WT-23 | "Blue in DB" | What is this on the approval page? Can you change the comment to be more descriptif (DB= database) | PD | yes | Yes | Enhanced the text (Charles)
2 | WT-24 | "Trasferred" | on the data approval page if a data sheet hasn't been approved yet it says "Transferred" can this say in complete or Not Approved or Pending? Pending Approval prefered | PD | yes | Yes | Changed to Pending approval
2 | WT-25 | Webtool default site page | In Web tools, when clicking on a subsector name, the system takes you to the site tab. Could it instead take you to the site tab analysis function by default (unclick analysis function if you want to see just the sampling station). Try a test to check the page loading speed | Report group | Yes | Yes/Maybe need group ok | Added another tab called "Analysis". Once on that tab, going to another subsector should automatically select that tab so less clicking…. I don't want it to be the automatic page loaded when people are browsing. (Charles)
3 | WT-2 | Map | There is a problem with the map. If you don’t open it first before making a sample plan, it boots you out of what you were doing and then you have to start all over again (doesn't delete the selections but you need to navigate back to sampling plan section). This needs to be fixed, you should be able to open the map at any point in the process | Lauren | yes
3 | WT-11 | High count report | E-mail could be sent to the Sanitary crew as well. (for all >500 MPN counts) | Pre-Arisc fall 2017 |  | yes | Added Joe Pomeroy to the list of people receiving emails.
3 | WT-14 | Year Files | Can we add some files to start storing sampling plans and reports per years. | Patrice | yes
4 | WT-8 | Contractor proposed calendar | Find a way (down the line) to have the contractor proposed schedualing and progress/run summary displayed in web tools somehow. Maybe add a run summary tab at the province level? | Patrice |  |  | combine with WT-7
| WT-1 | Edit Button | We don’t want to have such a layered structure in the web tool with the edit button function. Clicking edit to click edit is not efficient. We would like to have all of the buttons displayed right away | Lauren
5 | WT-3 | Sample Plan | We would like the ability to leave the sample plan/config file on the web tool so when using the input tool internally, we can just direct the input tool to find the file there. It would be much easier for us here at BIO. If anyone chnages the sample plan in the web tool, everyone will automatically have the updated copy. | Lauren
4 | WT-7 | High count report check box | Could we have a check box at the approval stage of a data sheet to confirm if the high count report was initiated (only applicable if counts over 500). Do we maybe want this at the input level since it's the responsibility of the lab to initiate this report | Patrice
Need webex call with Charles | WT-9 | Sampling site edit | When editing a sampling site location on the map by dragging, clarify to the users that they are in edit mode and also make the save button work (clicking save doesn't save the location, you have to click 'modify'). This will also help us not change station locations by accident- happend a few times while navigating in the map without realising you were in edit mode. | Patrice |  |  | More discussion required, hold off on this item. Is web tool the master file or Arc
WT-10
Need webex call with Charles | WT-21 | Web Tools name | Chris Roberts indicated that he doesn’t love the name "Web Tools". Should we consider possible name change? Yes | Greg/ NS
1 | WT-18 | Files tab | Within a year, in the files tab it would be nice to be able to pick the specific report you want for a year instead of all 2017 parameters. Enable us to pick the 'New analysis name' to create a report just with that. Make it easier to see parameters (files), easier to read and make sure it saves the parameters choosen. | Patrice |  | Yes | What is written in column D is not the way the system works. I did however show names of the "Save parameters for report" which can help you to visualized what the report will produced. (Charles)
4 | WT-27 | color schema location & Class Status Summary location | Can we make it look the same also (a solid block with letter in it)? This is to have class status stay next to %>43. If we can individually select for display (WT-12 &WT-17) | Dave M |  | Charles tried but the whole cell becomes red and it looks worst. | Needs consensus
4 | WT-28 | Report Writing | The save for reports button shoould be an Icon on top near the run selection | Dave M |  | Yes | did move some query options at the top. Group will need to discuss and agree on this (Charles)
| WT-29 | Runs used for stats | We need to come up with a different way to select the runs used for the calculation of the summary stats. Needs to treat all the stations as one | web tool group |  |  | ask Charles… will need more detail (Charles)
4 | WT-30 | Summary Statisics table | Name the FC summary table automatically based on the query | web tool group |  | Yes | On top of Wet-Dry-All it now gives number or runs used, do we want more info
1 | WT-31 | Tables for reports | Summary, FC, Salinity and temp tables should all show data based on the query, i.e, N=3X. For Discussion. The end year needs to be the same for all stations. Make sure that the cogs wheel option uses this as well. | Greg | Hell Yeah! | yes | The group will need to re-discuss this one. Is now showing the used runs and samples (Charles)
| WT-32 | Queries by type | Would be nice to have ability to do a water quality query by type (routine, CMP, etc). This would allow the exdclsuion of, say cmp runs from routine runs and thereby minimize having to click a bunch of runs off. | Greg
| WT-33 | Selection of N from MWQM Sites tab | Would it be possible to have the option to select the desired N from the MWQM Sites tab prior to selecting the analysis button? Currently, if you select 10, 15, 20, 25, 30, 35, 40 on the sites tab, it is only applicable to the sites page. If you select "15" and proceed to the analysis page, N=30 still defaults so you have to wait for that to load and then select N=15 and wait for that to load. This tend to get frustrating when working with larger subsectors. | Shelley

## Reports
Item Number (ex. R- #) | Item | Description | Contact Name | Resolved (Yes or No) | Comments
| Annual report | Can we only save the 'parameters' and calll that a report so we don't have to save a pdf (this applies to uneventfull years, like an annual/data report).
R-2 | automated naming | Can the files could be named based on parameters selected? | Dave M
R-3 / WT-20 | Tracking Precip station for reporting | Speak with Charles to see if it is possible for the robo report to indicate the source of precip info for given years and/or runs. Maybe use MSC station ID/ ASGAD/ Manual Entry? | Greg
R-4 | Discussion/Philosophy/TBD | Groups suggest that the auto-report should have one template that emcompasses 99% of our report. Minimising the amount of customised versions floating around. | Group
R-4b | Discussion/Philosophy/TBD | Minimise the customability so there is more uniformity. 2 types of reports (one without reclass and one with) is maximum. | Group
R-5 | Discussion/Philosophy/TBD | The first paragraph should be the most important info and the rest of the info follows (stating with a bang). | Group
R-6 | Discussion/Philosophy/TBD | Section 8 shold be removed and only what was presented at ARISC for a reclass is mentioned once. | Group
R-6 | Add on | Could include a link to the DFO mapping site to show new classification. Instead of describing current classification, refer to DFO website with link in Section 1 | Group | Group agreeance | If we don't ned this the executive summary may not need to be so descriptive.
R-7 |  | Lots of discussion on how many report formats we need : Re-evaluation, Annual/File review and comprehensive report. Seems to be a preference for annuals being a small one page (like executive summery section 1 with Tick boxes : water quality assessed= yes, sanitary assessed = yes, etc.) for annual reports (like BC) and having another format for when there are reclassifications. | Group | Group agreeance | The annual will have the executive summary but also a map and the stat summary table.
AR-8 |  | Do a comprehensive for subsectors that have not have a reclassification and only file reviews after. Could have electronic signature on file reviews at the bottom? | Group
AR-9 |  | Could have electronic signature on file reviews at the bottom? | PG
R-10 |  | Would like Web tools to take some sections from previous reports (such as results and discussion) and paste those in the appropriate sections of the next report. | Group | Yes
R-10 |  | Maybe combined the hydrographic and growing area description together | Patrice | not conclusive at all
R-11 |  | Want a section in the discussion for sanitary and water quality and waste waste treatment with a conclusion at the end. Be careful with text style for contradictions. Verify that sanitary sections are fact and not opinions. | Dave Curtis | Yes

## Web tool Auto-Report
Priority | Item Number (ex. R- #) | Item | Description | Contact Name | Resolved (Yes or No) | Comments
1 | AR-1 | Save | Save function often does not work. Need to save a second time | JAR/PG | yes | Did fixed the issue. Let me know if it happens again (charles)
2 | AR-2 | automatic texte | Line of text (copy of full report etc) shows up on many pages of the report. Please remove | JAR/PG | N/A | Can't find what this is about
1 | AR-3 | Font | Need a way to standardize title fonts and text fonts (set a default) | JAR/PG | Yes/partial | Do not copy any information directly from Word. When you copy information to the section, it should be as plain text. When the group decides on a font to use (font family and size) it will be set as the default font family and size. At this time the default font family is Arial and it's size is 10.
1 | AR-4 | Delete section | Bug with two sections in Re-evaluation report. Can't delete (we changed the titles of the buggy ones so you can see) | JAR/PG | yes | Note: You need to delete all text related to the year under the section before being able to delete the section
2 | AR-5 | Need a list of tags | Need a list of tags other then tables such as maps saved in the file section (maps from ARCGIS) and also tags to insert subsector name and code automaticly | JAR/PG | partial/continuing | Started (see Tag List tab) will need to update as we go
2 | AR-6 | Landscape option | Need option to put certain pages in landscape formart | JAR/PG | future | Todo Charles
4 | AR-7 | ECCC MWQM | Change all EC logos to ECCC and change program name once decided | JAR/PG | continuing | Will be done as we work on the standardized document
2 | AR-8 | Table and figures titles | Table titles should be on top and figures bellow. Will need a way to be able to change the figure or table number automaticly if some are deleted. Should the titles not be 'hardwired' into the table of figure code? | JAR/PG | Yes | At this time the table title and figure title will be hard wired when the tables and graphics/figures are created. Table of content, list of tables and list of figures are all created automatically from the content of the document. List of appendices is not working at this time.
2 | AR-9 | Copy feature | Will be used at the start but would be nice to have a copy feature to copy a whoe report template (let's say BC wants to take ours and modify it and call it a BC Re-evaluation). Same feature we have with sampling plan- can copy and rename | JAR/PG | maybe N/A | Postponed. Knowing that most of the section order and text would be different, it might not be worthwhile. To be discussed by the group.
1 | AR-10 | Character limit | Is 10 000 currently, need much more for large sections such as introduction. | JAR/PG | yes | Increased the limit to 100000 characters
2 | AR-11 | Formating | Why is the text not being inputted at the start of the page (always a 'return' too many at the top of each page). Could look at standardizing margins by default. | JAR/PG | yes | ¦¦¦PAGE_BREAK¦¦¦ should always be by itself on one line
3 | AR-12 | Question | What are the last lines at the end…seems like the same thing repeated a couple of times. Do we need this? | JAR/PG | yes | removed --- was only used for debugging purpose
1 | AR-13 | Report creating lag | Report not being created (stuck at 15%) for Baie de Tracadie | JAR/PG | yes | debugged --- pol source site which had no information was causing an error

## Tag List
Tag | Implemented | Description
Content General
¦¦¦TABLE_OF_CONTENT¦¦¦ | Yes | Will create a table of content in Word (All H1 to H6 will be inserted in the ToC)
¦¦¦LIST_OF_FIGURES¦¦¦ | Yes | Will create a list of figures from the figures caption found in the document
¦¦¦LIST_OF_TABLES¦¦¦ | Yes | Will create a list of tables from the tables caption found in the document
¦¦¦LIST_OF_APPENDICES¦¦¦ | No | Will create a list of appendices from the appendices in the document (should this be removed?)
Content Subsector
¦¦¦SUBSECTOR_FULL_REPORT_COVER_PAGE¦¦¦ | Yes | Will create the cover page of the full report/re-evaluation report
¦¦¦SUBSECTOR_FC_SUMMARY_STAT_ALL¦¦¦ | Yes | Will create the FC Summary statistics with all runs (wet or dry) with the exception of anything you would have identified to be removed for stat calculation (red run date in analysis)
¦¦¦SUBSECTOR_FC_SUMMARY_STAT_WET¦¦¦ | Yes | Will create the FC Summary statistics with all wet runs
¦¦¦SUBSECTOR_FC_SUMMARY_STAT_DRY¦¦¦ | Yes | Will create the FC Summary statistics with all dry runs
¦¦¦SUBSECTOR_MAP_ACTIVE_MWQM_SITES¦¦¦ | Yes need work | Will create a temporary map of all the active MWQM Sites for the subsector
¦¦¦SUBSECTOR_MAP_ACTIVE_POL_SOURCE_SITES¦¦¦ | Yes need work | Will create a temporary map of all the active MWQM Pollution source sites for the subsector
¦¦¦SUBSECTOR_MWQM_SITES_DATA_AVAILABILITY¦¦¦ | Yes | Will create a table showing the availability of data by year
¦¦¦SUBSECTOR_MWQM_SITES_NUMBER_OF_SITES_BY_YEAR¦¦¦ | Yes | Will create a graphic showing the number of sites monitored by year
¦¦¦SUBSECTOR_MWQM_SITES_NUMBER_OF_RUNS_BY_YEAR¦¦¦ | Yes | Will create a graphic showing the number of runs by year
¦¦¦SUBSECTOR_MWQM_SITES_NUMBER_OF_SAMPLES_BY_YEAR¦¦¦ | Yes | Will create a graphic showinig the number of samples analyzed by year
¦¦¦SUBSECTOR_MWQM_SITES_FC_TABLE¦¦¦ | Yes | Will create a table showing all the FC data (this tag needs to be below all the ¦¦¦SUBSECTOR_FC_SUMMARY_STAT_yyy¦¦¦ to work properly)
¦¦¦SUBSECTOR_MWQM_SITES_SALINITY_TABLE¦¦¦ | Yes | Will create a table showing all the salinity data (this tag needs to be below all the ¦¦¦SUBSECTOR_FC_SUMMARY_STAT_yyy¦¦¦ to work properly)
¦¦¦SUBSECTOR_MWQM_SITES_TEMPERATURE_TABLE¦¦¦ | Yes | Will create a table showing all the temperature data (this tag needs to be below all the ¦¦¦SUBSECTOR_FC_SUMMARY_STAT_yyy¦¦¦ to work properly)
¦¦¦SUBSECTOR_POLLUTION_SOURCE_SITES¦¦¦ | Yes need to subdivide | Will create some documentation for MWQM Pollution source sites (need to be subdivided more)
¦¦¦SUBSECTOR_MUNICIPALITIES¦¦¦ | No | Will create some documentation for each municipality within the subsector using the document type unique code "SubsectorMunicipalityDocx" under subsector
Content Municipality
¦¦¦MUNICIPALITY_MAP_INFRASTRUCTURE¦¦¦ | No | Will create a temporary map showing the infrastructure of the municipality
¦¦¦MUNICIPALITY_CONTACTS¦¦¦ | No | Will create a list of contacts and their roles with the management of the municipality infrastructure
¦¦¦MUNICIPALITY_INFRASTRUCTURE_DETAIL¦¦¦ | No | Will create a list of infrastructure showing the detail of each (i.e. which one is pumping to the other, description, flows, etc... )
Formating
¦¦¦PAGE_BREAK¦¦¦ | Yes | Will insert a page break in the word document ex: it's like pressing ctrl+ENTER in Word
¦¦¦LANDSCAPE¦¦¦ | No | Will change the page layout to landscape
¦¦¦PORTRAIT¦¦¦ | No | Will change the page layout to portrait
Variables
¦¦¦SUBSECTOR_NAME_SHORT¦¦¦ | No | Will insert the short name of the subsector ex: NS-01-010-001
¦¦¦SUBSECTOR_NAME_LONG¦¦¦ | No | Will insert the long name of the subsector ex: NS-01-010-001 (Baie Verte)
¦¦¦PROVINCE_NAME¦¦¦ | No | Will insert the full province name ex: Nova Scotia
¦¦¦PROVINCE_INITIAL¦¦¦ | No | Will insert the initial of the province name ex: NS
¦¦¦MUNICIPALITY_NAME¦¦¦ | No | Will insert the municipality name ex: Bouctouche