## Input Tool
Priority | Item Number (IT- #) | Item | Description | Contact Name | Group approved | Resolved (Yes or No/Date) | Comments
1 | IT-4 | Changing the date of a datasheet | We need to be able to change the date on the “datasheet” after you have started entering data without having to click F2. Remove the F2 function so it's easier to change date | Lauren | Yes | Yes | The user can only change the date of the lab sheet if the lab sheet is of type changed i.e. file name ending with (_C.txt). (_S.txt - sent, _F.txt - fail, or _A.txt - approve) will not allow you to change the date of the lab sheet. (Charles)
1 | IT-6 | Pop up when changing sent/accepted sheet | When changing or adding a duplicate with the F-functions on a sheet that is in sent or accepted mode, there is no pop up alerting the user to resend the data | Julie | yes | Yes
1 | IT-10 | R-log calculation error | It has been noticed that ‘sometimes’ the R-log daily duplicate value is not calculated correctly. For example, MPN duplicate combo of 1.9 and 2.0, R log is calculated as 0.30103 within the input tool but it should be 0.0223. | NL | yes | Yes | It was because the calculation was done with 1.0 and not 1.9. (Charles)
1 | IT-11 | Calendar is inconvenient. | When entering data for a run conducted in a previous month, you can only go back a single month at a time and the drop down closes. This is not great when entering May data, say in October. If calendar can not be changed, SOP should be updated to include calendar selection process described by Charles in the email. | NL | Yes | N/A | Charles: Put explenation in SOP
1 | IT-13 | "Processed by" field for daily duplicates | All data self populates based on the original sample with the exception of FC data (which shouldn’t) and processed by initials (which should). This is a potential source of error that can easily happen. | NL | yes | Yes | Removed the auto-populate for the Process by. (Charles)
1 | IT-14 | Updating of daily duplicate info | Daily duplicate info doesn’t update if original sample data is changed which gives us an opening for error. For example, if you go back and change the salinity in the original, the duplicate info will not update unless you do so manually. | NL/NS | yes | Yes | Now the user can't edit the time, sal and temp of Daily dup, Intertech dup and Intertech read.
1 | IT-15 | TC First/Average | What is this? It appears to be referring to/calculating salinity in the input tool, not temperature. REMOVE FIRST AND AVERAGE, not a necessity and space could be used for water bath info. Charles you can use the space saved here to move the bath one info from the full version down bellow the field lab temps. | NL | yes | Yes
1 | IT-17 | cells change blue for changes | do we need the cells to change blue if changes are during the initial data entry. I thought it was only after it was sent and changes were made that they turned blue. Changes revelance is being lost. Could it only track changes once you leave a sheet and come back to it? | NS | yes | yes | Log writing now only happens if you loose focus on the current lab sheet. This can happen when you want to close the application, when you log off, when you go to archive (directly or indirectly (selecting different date or subsector)) etc… (Charles)
1 | IT -19 | "send to server" | When you enter your data and hit "send to server" it takes you to another page with detail logs and programming details. Can it be a quick box with "are you sure you want to send to server?" on the same page as the data entry rather than take you to separate page. If not the separate page should highligh the send button .. why is there a "send to server" button if it doesnt do anything. Or the pop up box could also ask if you want to see the changes or details. | NS | yes | Yes | This sheet is there at our request. This step is between sending it and overwritting something by accident. We need to check this screen before sending but it most cases, there will be no differences so the extra screen will not show up. He will put the cancel and send button in color so that we see it easier.
1 | IT-20 | data entry page drop down beside date | identify what the drop down from 1-20 is … runs? Students have mistaken this for sampling day and other could think of using this as run 1 of 5 instead of it's intended use. Could we add some text next to it (multiple runs same day) or in the help button? | NS | yes | Yes | Added some text around the run number selection. (Charles)
1 | IT-21 | negative temperatures | negatives can be entered but show as red, asked if you want to accept and when you do it shows site- type in RED but removes the negative temperatures and no email is sent for approval. NB also: Contractors reported not being able to put (minus) temperatures in the input tool. I tried also and we can't (put's it in red) . This was ITEM WT 6 before. Moved to this list | NS/NB | yes | yes | New limit is now -12 degree Celcius. (Charles)
2 | IT-2 | Error in log record (light version) | In the light version of input tool, the log shows that two coolers were used. There is no option for multiple coolers so this should just be left out of the contractor version. | Lauren | Yes | yes | Corrected with IT-17 (new log system) (Charles)
2 | IT-5 | Tides | My contractors may not have internet access all the time so they may have to manually type in the tide cycle. Please add an example of the correct tide cycle format beside the tide entry field. Either put it directly next to box or in a help button | Lauren | Yes | Yes | Setting focus on the text box will show you an example of how to enter tides manually. We should encourage the use of the Get Tide button. Just before they send the sheet, they can get the tide using the button since at that time they would have access to the internet. (Charles)
2 | IT-9 | Auto Tab | The auto tabbing feature (for full version) needs to be consistent. The flow is not great when some fields auto tab and others don’t. We thought we would get used to it but never did. We recommend that the auto tab feature for bath incubation times and control results be removed. | NL | yes | Yes | New system: To move to the next item to enter you can press TAB or press ENTER. To move to the previous item you can press SHIFT+TAB or press CTRL+ENTER. I've remove every automatic refocussing. (Charles)
3 | IT-1 | Add drop down option for duplicates (light version of input tool) | Hold of on this item-more discussion about how to handle duplicate data...We need to have a drop down option for adding an intertech duplicate sample or changing the duplicate number. Hitting F2 and F3 is not user friendly, we want an obvious visual button to click on. | Lauren | Yes- NS to expand | yes | When focus in on the Grid and first column, the user will see some helping text at the bottom of the application (Status bar). This should help the user with the hidden functions (F2 - set Daily Duplicate, F3 - add or remove Intertech Duplicate, F4 - add or remove Intertech Read, F5 - add another sample) (Charles)
3 | IT-3 | Emails | When a datasheet is edited/changed, after being previously sent to the web tool, and you re-upload/re-send it, the auto generated email should say “revised or modified lab sheet sent” instead of “new” | Lauren | Yes | Pending…
3 | IT-7 | Highlighting Site-Type column when working in a row | We think that it would useful if the Site-Type column could become ‘highlighted’ when working in any cell within the row because it is difficult to see what site you are working with when, for example, entering data in comments field. This would be useful for data entry QC process as well. | NL | yes | Yes
3 | IT-12 | Placement of bath incubation times | When using multiple baths, why are bath 1 and 2 incubation times in different areas? Bath 2 incubation time should be moved over underneath Bath 1. Brain strom on reorginasing things if possible espicially concidering more space will be available due to IT-15 | NL | yes | Yes | By removing the TC average and First TC, we now have enough room to show all bath incubation time on the left. (Charles)
3 | IT 22 | interface layout - main page | label of the drop down menus and create some separation between creating new sheets and searching existing sheets. (in the archive section, there is room to add some text) | NS | yes | Yes | Had to keep the second row with the Subsector list, Date and Runs… Did reformat a bit. (Charles)
No action needed | IT-8 | Mandatory entry of site sampling time. | While sampling time should always be recorded in the field, we had an occasion this summer where a student forgot to record this data. This created a challenge for data entry. To make it work, we had to estimate sample times. Hopefully this never happens again but it is always possible. Thoughts on how to deal with this? Suggest estimating time and noting it in the comments?? PD. Write this in the Data entry SOP | NL | yes | N/A | Added this to the document review excell for 2018
| IT-24 | Duplicate samples | We need to be able to delete duplicate samples if there weren't any for a particular run. Hit F2 again maybe? | NS |  | yes | Added the same functionallity as Intertech Duplicate and Intertech Read. Now to change the Daily Duplicate. You first need to remove the existing one by pressing F2 while have focus on the grid first column. Then you need to add the new one by pressing F2 while having focus on the grid first column. (Charles)
| IT-25 | Archive layout | would it be possible to have the subsector numbers and names listed in the archive in bold text so it stands out better? | NS |  | Yes | Can't have different style between items in the list. I did however made it a bit better visually… added a bit more space between subsectors… Still open for suggestions... (Charles)
| IT-996 | Red flags | Some flags not staying red when you lof off | NB |  | Yes | When typing the time in wrong (for example), it would put it in red but the next time you logged in, the red was gone or the value was replaced with 00:00, potential for sending this before correcting. Charles fixed this by deleting right away anythign typed wrong.
| IT-26 | Shared Archive | Do we need to see the shared archive path? Are we ever going to edit this in the input tool? If not, then can we remove it and have the pathway explained in the user manual for the input tool instead? It is taking up valuable space and I also think it will confuse contractors who don’t have this pathway as a backup (unless I have a misunderstanding of that). | NS |  | yes | Need to keep this. Will rename to something more appropriate and easier to understand. I suggest "Backup Directory". I'm also suggesting that we could have a parameter within the Sampling plan which would identify the "Backup Directory" to be used within the CSSPWQInputTool. (Charles)
| IT-27 | Open button | Do we need an “open” button when we can just double click on a run to see it? I don’t think I will need the button and again it’s taking up space. | NS |  | Kept it for now | I would like to keep this button for now. New contractors/users might need it before they find out that they can double click. (Charles)
| IT-28 | Placement of button and items | I rearranged the placement of where the buttons/drop downs are located to flow a bit more with the order of which the user needs to use the tool. Ex. Hit “Update Dataset” before doing any data entry, then the user will either want to create a new run or search for a file…. Ideally I’d like to have the search function over to the right a lot more but I know Charles has made comments about limited screen resolution in the past so wasn’t sure if that would be an option. | NS |  | Yes | Implemented your suggestions with minor modification. Did have to keep that second line (Subsector, Date, Run…) (Charles)
| IT-29 | Reduce the log info if possible | I’d like to simplify what shows up in the log. I don’t want or need to see the CSSP grid information, I only want to see from the sample number over to the right. See attached. | NS |  | Yes | This text is needed to be able to color items that have been changed since the last official save. Will need to keep it… for now anyway… Hope you can live with the extra text in the log. (Charles)
1 | IT-30 | MPN value change | New standard methods changed the value for tube combination 1-4-0 (was MPN = 10, please change to MPN 11) | group | yes | Yes
1 | IT-31 | TC now back to 10oC | In full version, criteria for TC sample rejection is anything above 10oC. | GROUP | yes | yes
| IT-32 | Change subsector on datasheet | Once the datasheet entry has begin, there is no way to change the subsector to a different one if you pick the wrong subsector in error. This will create a lot of extra datasheets on the "home" page that are not needed and cause confusion | NS | no | N/A | Will implement delete function to deal with this. See next IT
1 | IT-33 | Delete button | Delete button in the 'data sheet' window. Delete from local and back drives (change file name to delete but keeps it in the folder but not in input tool Home list) | Group | yes but need to confirm that it's ok if this only works when online. | yes
1 | IT-34 | Email | Customizing option for who receives what email and at what frequency. Option to add contractor emails. To be implementing directly in sampling plan. | Group | Yes | yes | Sampling plan completed within CSSPWebTools. Now we need to do all the emails in both official languages. (Charles)
2 | IT-35 | Changed status to 'in progress' | Preference for the term 'in progress' instead of 'changed'. | Group | Yes | Postpone | Charles suggested to keep this for next fall as it will mean lots of changes and not enough time to debug before start of season
1 | IT-34 | New path option for backup folder | Make sure this is still editable by users and add a 'save' function so that if it's modified in the input tool, it saves it to the sampling plan. | Group | Yes | yes

## Web Tool
Priority | Item Number (ex. WT- #) | Item | Description | Contact Name | Group approved | Resolved/ Date (Yes or No) | Comments
1 | WT-4 | Error message when accepting a datasheet | Error message when trying to accept a previously accepted datasheet. Same date just different sample data. Possible cause was a change in the list of stations-we added two stations in between accepting the first datasheet and the second acceptance. | Lauren | yes | Ongiong…..Was not able to recreate error | I will need to do more test on this. But for now I can't reproduce the error. (Charles)
1 | WT-13 | FC Data table | When you remove a run (removed from statistics) can you hide it in the table, it is still showing currently) | Pre-Arisc fall 2017 | yes | No… maybe (see WT-31) | This one will depends on the way we will show raw data in the reports (need group discussion). If the group still wants this to be the case it can be done…Same for WT-31 it should be removed or invisible from the table raw data.
1 | WT-16 | Stats table -report | In the full report on at the bottom of the Summary stats table you see the end date as 1985, should be last year in stats. | Pre-Arisc fall 2017 | yes | No, need to check. | Should reflet points WT-31, the querry dictates the date here.
1 | WT-22 | ASGAD Precip | Need to be able to select "ASGAD" as a precip source on the Climate sites tab | Greg | yes | Later
1 | IT-16 | File summary bubble (ie sample plan) | Grey total number of files being tracked is not reflected in the bubble | NS | yes | Later | These gray bubbles are recalculated once in a while for now because we are still importing a lot of data from ASGAD and others. Later all these bubbles will be calculated automatically. It's already in the system, I just removed it temporarily. (Charles)
2 | WT-5 | Sampling plan | Can the MPN, water and lab selection be done in the sampling plan first so it shows up by default but still have the option to change it at the acceptance stage? (you only have to select it once per subsector at the moment but when you have a new sampling plan, you have to do it again) Agreed! | Julie/ NS | yes | Yes | Now possible to set defaults of Analyze method, Sample matrix and Laboratory within the setup of the Sampling Plan. These will then be the defaults when accepting or rejecting Lab sheets. (Charles)
3 | WT-2 | Map | There is a problem with the map. If you don’t open it first before making a sample plan, it boots you out of what you were doing and then you have to start all over again (doesn't delete the selections but you need to navigate back to sampling plan section). This needs to be fixed, you should be able to open the map at any point in the process | Lauren | yes | Partial | The saving of the information in the Sampling Plan has been subdivided. So less chance of loosing unsaved information. Will continue to think of a way to reload the map without reloading the page and change the URL (Charles).
3 | WT-14 | Year Files | Can we add some files to start storing sampling plans and reports per years. | Patrice | yes |  | Ongoing
4 | WT-8 | Contractor proposed calendar | Find a way (down the line) to have the contractor proposed schedualing and progress/run summary displayed in web tools somehow. Maybe add a run summary tab at the province level? | Patrice |  |  | combine with WT-7
4 | WT-1 | Edit Button | We don’t want to have such a layered structure in the web tool with the edit button function. Clicking edit to click edit is not efficient. We would like to have all of the buttons displayed right away | Lauren |  | Next version or COTS | If ever we (or COTS) develop a new version, there might be ways to simplify it a bit. It's still going to be a challenge because of the amount of information residing in each web page.
5 | WT-3 | Sample Plan | We would like the ability to leave the sample plan/config file on the web tool so when using the input tool internally, we can just direct the input tool to find the file there. It would be much easier for us here at BIO. If anyone chnages the sample plan in the web tool, everyone will automatically have the updated copy. | Lauren |  | Not recommended | Suggest not going this direction (Charles). For simplicity and backup of sampling plan files. Having all inhouse staff using the same sampling plan document might not be something we want. (Charles)
4 | WT-7 | High count report check box | Could we have a check box at the approval stage of a data sheet to confirm if the high count report was initiated (only applicable if counts over 500). Do we maybe want this at the input level since it's the responsibility of the lab to initiate this report | Patrice
Need webex call with Charles | WT-9 | Sampling site edit | When editing a sampling site location on the map by dragging, clarify to the users that they are in edit mode and also make the save button work (clicking save doesn't save the location, you have to click 'modify'). This will also help us not change station locations by accident- happend a few times while navigating in the map without realising you were in edit mode. | Patrice | Yes |  | More discussion required, hold off on this item. Is web tool the master file or Arc Ongoing.
Need webex call with Charles | WT-21 | Web Tools name | Chris Roberts indicated that he doesn’t love the name "Web Tools". Should we consider possible name change? Yes | Greg/ NS | Yes |  | Wait for new section names, and see if it is a country wide system but yes let's look into it.
1 | WT-18 | Files tab | Within a year, in the files tab it would be nice to be able to pick the specific report you want for a year instead of all 2017 parameters. Enable us to pick the 'New analysis name' to create a report just with that. Make it easier to see parameters (files), easier to read and make sure it saves the parameters choosen. | Patrice |  | Yes | What is written in column D is not the way the system works. I did however show names of the "Save parameters for report" which can help you to visualized what the report will produced. (Charles)
4 | WT-27 | color schema location & Class Status Summary location | Can we make it look the same also (a solid block with letter in it)? This is to have class status stay next to %>43. If we can individually select for display (WT-12 &WT-17) | Dave M |  | Charles tried but the whole cell becomes red and it looks worst. | Needs consensus
1 | WT-31 | Tables for reports | Summary, FC, Salinity and temp tables should all show data based on the query, i.e, N=3X. For Discussion. The end year needs to be the same for all stations. Make sure that the cogs wheel option uses this as well. | Greg | Yes | yes | The group will need to re-discuss this one. Is now showing the used runs and samples (Charles)
| WT-32 | Queries by type | Would be nice to have ability to do a water quality query by type (routine, CMP, etc). This would allow the exclsuion of, say cmp runs from routine runs and thereby minimize having to click a bunch of runs off. | Greg | Yes |  | We all agree that this would be usefull (Agree Charles) At this time the statistical/analysis is only using the Routine runs by default. We need to be able to use other type of runs. (Charles)
| WT-33 | Selection of N from MWQM Sites tab | Would it be possible to have the option to select the desired N from the MWQM Sites tab prior to selecting the analysis button? Currently, if you select 10, 15, 20, 25, 30, 35, 40 on the sites tab, it is only applicable to the sites page. If you select "15" and proceed to the analysis page, N=30 still defaults so you have to wait for that to load and then select N=15 and wait for that to load. This tend to get frustrating when working with larger subsectors. | Shelley |  | n/a | Not applicable anymore since we have the MWQM sites and the Analysis in two difference tabs (Charles)
| WT-34 | Parameters Saved | Parameters already saved in the drop down combo box should show up in the analysis when clicked. | Group | Yes | yes | Can we save the word and excel files as the same name? You can put an E or W to differenciate the documents (Charles) ---- We also need to semi-automate the naming of these saved parameters as suggested by Dave and Greg
| WT-35 | Cog Wheel | From the cog wheel can we pick one option and then create from it. | group | Yes
5 | WT-36 |  | Can the map pop up on the split screen | Group
| WT-37 | Site tab | In the site page can we show more i.e. sub-sector info. | Goup | yes
| WT-38 |  | T on by default (number first and then letter) | group | yes
1 | WT-39 | MPN value change | New standard methods changed the value for tube combination 1-4-0 (was MPN = 10, please change to MPN 11) | group | yes | Yes
1 | WT-40 | Formatting excel data output | Redesign the formatting of the excel output | group | yes
5 | WT-41 | rounding of temp and salinity values | can we keep the actual value for the temp and salinity that is recorded in the field on the analysis tab as is shown on the run tab | group | yes | yes | low priority
| WT-42 |  | Dave Curtis is looking to know which Climate Sites is being used for each subsector and year and potentially data |  |  | yes | every single value of precipitation will have a superscript letter identifying the climate site

## Reports
Item Number (ex. R- #) | Item | Description | Contact Name | Resolved (Yes or No) | Comments
| Annual report | Can we only save the 'parameters' and calll that a report so we don't have to save a pdf (this applies to uneventfull years, like an annual/data report).
R-2 | automated naming | Can the files could be named based on parameters selected? | Dave M
R-3 / WT-20 | Tracking Precip station for reporting | Speak with Charles to see if it is possible for the robo report to indicate the source of precip info for given years and/or runs. Maybe use MSC station ID/ ASGAD/ Manual Entry? | Greg | Yes | every single value of precipitation will have a superscript letter identifying the climate site
R-4 | Discussion/Philosophy/TBD | Groups suggest that the auto-report should have one template that emcompasses 99% of our report. Minimising the amount of customised versions floating around. | Group
R-4b | Discussion/Philosophy/TBD | Minimise the customability so there is more uniformity. 2 types of reports (one without reclass and one with) is maximum. | Group
R-5 | Discussion/Philosophy/TBD | The first paragraph should be the most important info and the rest of the info follows (stating with a bang). | Group
R-6 | Discussion/Philosophy/TBD | Section 8 shold be removed and only what was presented at ARISC for a reclass is mentioned once. | Group
R-6 | Add on | Could include a link to the DFO mapping site to show new classification. Instead of describing current classification, refer to DFO website with link in Section 1 | Group | Group agreeance | If we don't need this the executive summary may not need to be so descriptive.
R-7 |  | Lots of discussion on how many report formats we need : Re-evaluation, Annual/File review and comprehensive report. Seems to be a preference for annuals being a small one page (like executive summery section 1 with Tick boxes : water quality assessed= yes, sanitary assessed = yes, etc.) for annual reports (like BC) and having another format for when there are reclassifications. | Group | Group agreeance | The annual will have the executive summary but also a map and the stat summary table.
AR-8 |  | Do a comprehensive for subsectors that have not have a reclassification and only file reviews after. Could have electronic signature on file reviews at the bottom? | Group
AR-9 |  | Could have electronic signature on file reviews at the bottom? | PG
R-10 |  | Would like Web tools to take some sections from previous reports (such as results and discussion) and paste those in the appropriate sections of the next report. | Group | Yes
R-10 |  | Maybe combined the hydrographic and growing area description together | Patrice | not conclusive at all
R-11 |  | Want a section in the discussion for sanitary and water quality and waste waste treatment with a conclusion at the end. Be careful with text style for contradictions. Verify that sanitary sections are fact and not opinions. | Dave Curtis | Yes

## Auto-Report Reclass
Priority | Item Number (ex. R- #) | Item | Description | Contact Name | Resolved (Yes or No) | Comments | Charles comment
2 | AR-3 | Font | Need a way to standardize title fonts and text fonts (set a default) | JAR/PG | Yes/partial | Do not copy any information directly from Word. When you copy information to the section, it should be as plain text. When the group decides on a font to use (font family and size) it will be set as the default font family and size. At this time the default font family is Arial and it's size is 10. | Adressed during demo, at next meeting
2 | AR-5 | Tag list | Need a list of tags other then tables such as maps saved in the file section (maps from ARCGIS) and also tags to insert subsector name and code automaticly. | JAR/PG | partial/ continuing | Started (see Tag List tab) will need to update as we go
2 | AR-9 | Copy feature | Will be used at the start but would be nice to have a copy feature to copy a whole report template (let's say BC wants to take ours and modify it and call it a BC Re-evaluation). Same feature we have with sampling plan- can copy and rename | JAR/PG | maybe N/A | Postponed. Knowing that most of the section order and text would be different, it might not be worthwhile. To be discussed by the group. | Will require Charles intervention. Is not possible by the user.
1 | AR-15 | List of Tables | Table 6.2.0a should be Table: 6.2a Summary FC Densities (MPN/100ml) and nothing else | JAR | n/a | See AR-21 | Table numbering should be automatic and done at the end of wrinting of the report. Same with Figure numbering. CL will try and find a way.
1 | AR-16 | Table Appendix (list of tables) | Titles should be ' Table A 1.0, B 1.0' | DC |  | Remove the 'appendix' A from title and the '2' at the end
1 | AR-18 | Figure 4.2.0 | Figure name should be 'Figure 4.2.0 - ¦¦¦MUNICIPALITY_NAME¦¦¦ Wastewater Treatment and Collection System. | JAR |  | To do before next meeting ¦¦¦SUBSECTOR_MUNICIPALITIES¦¦¦
1 | AR-20 | Figure 4.3 | Should be called 'Figure 4.0 - Pollution Sources Sites Location' | JAR |  | This should be a map that includes non-point and point source pollution (ei: includes LS, TP, OF).
1 | AR-21 | Table 6.2.0a | Text should be size 10.5, in black and have a line under the first row and right of first column. Also, lamèque, bug with this table. 010A vs 10A and 014A vs 14A. Also NL 07-010-008, bug with station 0004 to verify | JAR/DC |  | Diccusion with group: would prefer Table 1a, 1b, etc) | Table numbering should be automatic and done at the end of wrinting of the report. Same with Figure numbering
1 | AR-22 | Table Appendix A 1.0 | Suggestion, Table should be named: Table A-1: FC Densities, next one should be Table A-2, etc | JAR/DC | Possibly, group decision | See comments in red AR-21, AR16, AR18
1 | AR-24 | Authors-cover page | Should we have the list of names instead of 'SWCP Staff' Add tag function to have list of authors per province | DC | yes | A tag would be created for to include all names (if you are in NL subsector, the tag will find NL author). We would need to check everytime to make sure it is good for that perticular year. | See tags ¦¦¦xx_AUTHORS¦¦¦
2 | AR-25 | Report ID-cover page | Would like to use the old numbering system for reports from library file. See also AR-41. | DC/GP |  | Was agreed that those who want that will type it in themselves, the rest will keep report ID as is and keep the month/year of productions to distinguish between two reports from same subsector written same year. NEW comment : Ask CL is he can create report ID similar to previous format. | to be discussed again. Current report ID ensures unique ID's (old format had missing info
2 | AR-26 | Abstract | Discussion on need for this section | DC/GP |  | Group seems in agrreance to remove this section altogether if there are no official requirements for it. Page 2 could serve as an abstract. PG will look into this. | Keep as is
1 | AR-27 | Table of content- page numbers | Need page numbering. Page 1 should be the executive summary. Page before that should be i, ii, iii, etc. Do we want i, ii, iii. Also do we want o have sub-sector name in footer like in old reports. | DC/GP |  | Group disc. Preface should be 'i' and page 1 would be seciton 1.0. Numbering bottom -centered | Implement header and footer.
1 | AR-29 | Figure 1.0 | Capitalize Survey Area in figure 1.0 title | GP |  |  | To do
1 | AR-31 | Section 1.0 and others | Extra spacing 'returns'. Bug form web tools when copying text over.Once the text is saved and you go back into the text, returns are added. Users has to remove them again and save a second time. | JAR/DC/GP |  | NOTE from Julie: I FIXED SECTION 1.0, now only need to fix figures | Probably within the text written "from 2016 report"
2 | AR-35 | Section 6.1 1985 reference | Was the intention of this paragraph to give a history of how things started. If so, how did the NSSP approve in 1978 of a method from 1985…so either we need to change the 1985 to the original method that the CSSP used OR we need to reference the correct method that is APHA Standard Methods For Examination of Water and Wastewater (2017) | JAR/DC |  | Need to check with DC and guidance doc (email sent to DC for guidance)
2 | AR-36 | Back page | Suggestion to remove Queen Square address. | DC |  |  | CL: Should use the generic email from NCO
1 | AR-38 | Salinity/Temp tables | Option to hide salinity and temp tables from report when generating the report in webtools. | PG |  |  | In parameters
1 | AR-39 | FC/Salinity/Temp Tables | remove number at end of FC-salinity and temp | JAR |  |  | To do
1 | AR-40 | List of Tables | List on page 6 is not being generated. | JAR/PG |  |  | To do
1 | AR-41 | Section 1.0 | Should we show report period or just report year. Alternatively do we want to have the report year on the cover page (yes, see AR53). | JAR/PG |  | Dicussion had: want report period instead of report year (range of data used in data analysis ex: 2005-2011. | To do. CL to create tag
1 | AR-46 | Background | Insert new decal template ECCC (header and footer) | KM |  | Too right for binding (see AR-51) | Will do once Julie sends new pics
2 | AR-49 | Rubber stamp | Should we show our administative changes to Chris to make sure that we respect the USFDA 'standard'/ 'requirements'. | PG
1 | AR-50 | Appendix D and E | Refer to another report instead of NA | CL |  | Ask Chris also if OK. More discussion here needed. Group would like N/A if no wastewater treatment plant or if there is, the information directly in report or a reference to another report. | Will work hard to implement all Munictipality and infrastructure information within reevaluation auto report
1 | AR-51 | Front Page, images | Move to the right to be able to bind. Should be in blocks, no overlap, Charles can add pictures. | CL |  |  | Will do once Julie sends new pics
1 | AR-53 | Cover page | Next to 'Re-Evaluation Report' insert the year of the last data set used in the report | Group |  | Year should appear right after "Re-Evaluation Report" Should be last year used in stats | To Do
2 | AR-55 | GD for Sanitary | General description to be added to the sanitary sections 4.3 and 4.4. | KM/JAR |  | Create 5 or so templates with the help of provinces to make sure they represents every provinces reality. KM TO DO
1 | AR-56 | Sanitary table | Adopt option 1 as the new sanitary table, remove Risk high and simply have Low, Moderate or High indicated. | KM |  | Ask Charles if removing work risk from table is possible. (See Karyne's example for details) | To Do
1 | AR-57 | Sanitary Summary | Include option to remove or keep this information | KM |  | Ask Charles about options (See Karyne's example) | To Do
1 | AR-58 | Sections 4.4.1 to 4.4.5 | Create generic text templates with tags to allows for self populating sanitary text. So the text could be added extra information on a yearly basis in Webtools. | KM |  | Create tags with Charles help. Karyne will update the sections with generic text and tell Charles what tags she needs | To do once Karyne gives list of tags
1 | AR-59 | Report Bilingual | Make sure that the french text is available for web tool to grab and populate. | PG/JAR |  |  | To Do (copy and rename)
1 | AR-63 | Appendix A, B ande C tables | Still data outside of N=30 showing up. Group would like all data in black and put blank any data not being used | Group |  | Will remove color (green) defince -- (no data) and n (not used) and remove dates where 0 data was used | To Do

## Tag List
Tag | Implemented | Description
Content General
¦¦¦TABLE_OF_CONTENT¦¦¦ | Yes | Will create a table of content in Word (All H1 to H6 will be inserted in the ToC)
¦¦¦LIST_OF_FIGURES¦¦¦ | Yes | Will create a list of figures from the figures caption found in the document
¦¦¦LIST_OF_TABLES¦¦¦ | Yes | Will create a list of tables from the tables caption found in the document
¦¦¦LIST_OF_APPENDICES¦¦¦ | No | Will create a list of appendices from the appendices in the document (should this be removed?)
Content Subsector
¦¦¦SUBSECTOR_RE_EVALUATION_COVER_PAGE¦¦¦ | Yes | Will create the cover page of the full report/re-evaluation report
¦¦¦SUBSECTOR_FC_SUMMARY_STAT_ALL¦¦¦ | Yes | Will create the FC Summary statistics with all runs (wet or dry) with the exception of anything you would have identified to be removed for stat calculation (red run date in analysis)
¦¦¦SUBSECTOR_FC_SUMMARY_STAT_WET¦¦¦ | Yes | Will create the FC Summary statistics with all wet runs
¦¦¦SUBSECTOR_FC_SUMMARY_STAT_DRY¦¦¦ | Yes | Will create the FC Summary statistics with all dry runs
¦¦¦SUBSECTOR_MWQM_SITES_DATA_AVAILABILITY¦¦¦ | Yes | Will create a table showing the availability of data by year
¦¦¦SUBSECTOR_MWQM_SITES_NUMBER_OF_SITES_BY_YEAR¦¦¦ | Yes | Will create a graphic showing the number of sites monitored by year
¦¦¦SUBSECTOR_MWQM_SITES_NUMBER_OF_RUNS_BY_YEAR¦¦¦ | Yes | Will create a graphic showing the number of runs by year
¦¦¦SUBSECTOR_MWQM_SITES_NUMBER_OF_SAMPLES_BY_YEAR¦¦¦ | Yes | Will create a graphic showinig the number of samples analyzed by year
¦¦¦SUBSECTOR_MWQM_SITES_FC_TABLE¦¦¦ | Yes | Will create a table showing all the FC data (this tag needs to be below all the ¦¦¦SUBSECTOR_FC_SUMMARY_STAT_(ALL,WET,DRY)¦¦¦ to work properly)
¦¦¦SUBSECTOR_MWQM_SITES_SALINITY_TABLE¦¦¦ | Yes | Will create a table showing all the salinity data (this tag needs to be below all the ¦¦¦SUBSECTOR_FC_SUMMARY_STAT_(ALL,WET,DRY)¦¦¦ to work properly)
¦¦¦SUBSECTOR_MWQM_SITES_TEMPERATURE_TABLE¦¦¦ | Yes | Will create a table showing all the temperature data (this tag needs to be below all the ¦¦¦SUBSECTOR_FC_SUMMARY_STAT_(ALL,WET,DRY)¦¦¦ to work properly)
¦¦¦SUBSECTOR_POLLUTION_SOURCE_SITES¦¦¦ | Yes need to subdivide | Will create some documentation for MWQM Pollution source sites (need to be subdivided more)
¦¦¦SUBSECTOR_POLLUTION_SOURCE_SITES_COMPACT¦¦¦ | Yes | Will create some documentation for MWQM Pollution source sites compact
¦¦¦SUBSECTOR_MUNICIPALITIES_COMPACT¦¦¦ | No | Will create some documentation showing each municipality and infrastructure hierarchy (only basic info)
¦¦¦SUBSECTOR_MUNICIPALITIES_FULL¦¦¦ | No | Will create some documentation showing each municipality and infrastructure hierarchy (full info) which include Contacts, each infrastructure detail info, outfall info, comments
Content Subsector Municipality
¦¦¦SUBSECTOR_MUNICIPALITY_INFRASTRUCTURE_MAP¦¦¦ | No | Will insert a graph placeholder or get an existing graph from CSSPWebTools Named: [{subsector}_{municipalityname}_Infrastructure_Map_{year}.png] and saved under Files of the Subsector
Formating
¦¦¦PAGE_BREAK¦¦¦ | Yes | Will insert a page break in the word document ex: it's like pressing ctrl+ENTER in Word
¦¦¦LANDSCAPE¦¦¦ | Yes | Will change the page layout to landscape
¦¦¦PORTRAIT¦¦¦ | Yes | Will change the page layout to portrait
Variables
¦¦¦SUBSECTOR_NAME_SHORT¦¦¦ | yes | Will insert the short name of the subsector ex: NS-01-010-001
¦¦¦SUBSECTOR_NAME_LONG¦¦¦ | yes | Will insert the short name of the subsector ex: NS-01-010-001
¦¦¦SUBSECTOR_NAME_TEXT¦¦¦ | yes | Will insert the long name of the subsector ex: Baie Verte
¦¦¦PROVINCE_NAME¦¦¦ | yes | Will insert the full province name ex: Nova Scotia
¦¦¦PROVINCE_INITIAL¦¦¦ | yes | Will insert the initial of the province name ex: NS
¦¦¦MUNICIPALITY_NAME¦¦¦ | yes | Will insert the municipality name ex: Bouctouche
¦¦¦STATISTICS_LAST_YEAR¦¦¦ | yes | Will insert the year of the report
¦¦¦NL_AUTHORS¦¦¦ | yes | D. Curtis, G. Perchard, M. Glavine
¦¦¦NB_AUTHORS¦¦¦ | yes | B. Richard, P. Godin, K. Martell, J. Pomeroy, C. LeBlanc, J.A. Richard
¦¦¦NS_AUTHORS¦¦¦ | yes | D. MacArthur, L. Pothier, R. Alexanders, P. Densmore
¦¦¦PE_AUTHORS¦¦¦ | yes | D. MacArthur, L. Pothier, R. Alexanders
¦¦¦STATISTICS_PERIOD¦¦¦ | yes | Will show the report period start and end year EX: 2019 - 2002
Other
¦¦¦SUBSECTOR_ECCC_AND_SWCP_LOGO¦¦¦ | yes | Will insert ECCC and SWCP logo
¦¦¦SUBSECTOR_CSSP_LOGO¦¦¦ | yes | Will insert CSSP logo
Maps
¦¦¦SUBSECTOR_LOCATION_OF_SURVEY_AREA_MAP¦¦¦ | yes | Will insert a draft map or get an existing map from CSSPWebTools Named: [{subsector}_Location_of_Survey_Area_Map_{year}.png] and saved under Files of the Subsector
¦¦¦SUBSECTOR_CURRENT_CLASSIFICATION_AND_SAMPLING_LOCATION_MAP¦¦¦ | yes | Will insert a draft map or get an existing map from CSSPWebTools Named: [{subsector}_Current_Classification_And_Sampling_Location_Map_{year}.png] and saved under Files of the Subsector
¦¦¦SUBSECTOR_RECOMMENDED_CLASSIFICATION_MAP¦¦¦ | yes | Will insert a graph placeholder or get an existing graph from CSSPWebTools Named: [{subsector}_Recommended_Classification_Map_{year}.png] and saved under Files of the Subsector
¦¦¦SUBSECTOR_POLLUTION_SOURCE_LOCATIONS_MAP¦¦¦ | yes | Will insert a graph placeholder or get an existing graph from CSSPWebTools Named: [{subsector}_Pollution_Source_Locations_Map_{year}.png] and saved under Files of the Subsector

## Completed items
Priority | Item Number (ex. WT- #) | Item | Description | Contact Name | Group approved | Resolved/ Date (Yes or No) | Comments
1 | WT-12 | Summary Statisics table | Can we add buttons to hide columns (i.e Max Fc, Colour coded class) | Pre-Arisc fall 2017 | yes | Yes | Resolved but may come back later.
1 | WT-15 | Stats | In the stats page (pile of wood), if you click to show temperature or salinity it would be nice to have a 'T' and an 'S' beside value | Patrice | yes | yes | Resolved
1 | WT-17 | Stats (same as WT-12) | Ability to hide the 260 (not used in NFLD) | Dave Curtis | yes | Yes | * And possibly other fields as well. Nice to have some user configurability options. I believe that NS also omits MAX FC (GP) see WT-12 (Charles)
1 | WT-19 | sample type drop down | selected or defaulted sample type should show on the top of the drop downlist. Can the one selected be bumped to the top. Also remove duplicate, intertech read/ intertech duplicate from this drop down list. This is actually "run type" | PD | yes | Yes/ongoing | Done
1 | WT-26 | duplicate comment on the webtool needs to be changed | The comment "Where duplicate results differ in value, the highest value will serve as the daily result and the lower value as duplicate result for QA/QC purposes." Recommended change would be "Where duplicate results differ in value, the higher result will be used in data computation." | NS | yes | yes/ongoing | Done
2 | WT-23 | "Blue in DB" | What is this on the approval page? Can you change the comment to be more descriptif (DB= database) | PD | yes | Yes | Done
2 | WT-24 | "Trasferred" | on the data approval page if a data sheet hasn't been approved yet it says "Transferred" can this say in complete or Not Approved or Pending? Pending Approval prefered | PD | yes | Yes | Done
2 | WT-25 | Webtool default site page | In Web tools, when clicking on a subsector name, the system takes you to the site tab. Could it instead take you to the site tab analysis function by default (unclick analysis function if you want to see just the sampling station). Try a test to check the page loading speed | Report group | Yes | Yes/Maybe need group ok | Yes done
3 | WT-11 | High count report | E-mail could be sent to the Sanitary crew as well. (for all >500 MPN counts) | Pre-Arisc fall 2017 |  | yes | Added Joe Pomeroy to the list of people receiving emails.
4 | WT-28 | Report Writing | The save for reports button shoould be an Icon on top near the run selection | Dave M |  | Yes | Done
| WT-29 | Runs used for stats | We need to come up with a different way to select the runs used for the calculation of the summary stats. Needs to treat all the stations as one | web tool group | yes | yes | Covered elsewhere
4 | WT-30 | Summary Statisics table | Name the FC summary table automatically based on the query | web tool group |  | Yes | Done
Priority | Item Number (ex. R- #) | Item | Description | Contact Name | Resolved (Yes or No) | Comments
1 | AR-1 | Save | Save function often does not work. Need to save a second time | JAR/PG | yes | Did fixed the issue. Let me know if it happens again (charles)
1 | AR-4 | Delete section | Bug with two sections in Re-evaluation report. Can't delete (we changed the titles of the buggy ones so you can see) | JAR/PG | yes | Note: You need to delete all text related to the year under the section before being able to delete the section
2 | AR-6 | Landscape option | Need option to put certain pages in landscape formart | JAR/PG | Yes | See tag list
4 | AR-7 | ECCC MWQM | Change all EC logos to ECCC and change program name once decided | JAR/PG | Yes
2 | AR-8 | Table and figures titles | Table titles should be on top and figures bellow. Will need a way to be able to change the figure or table number automaticly if some are deleted. Should the titles not be 'hardwired' into the table of figure code? | JAR/PG | Yes | At this time the table title and figure title will be hard wired when the tables and graphics/figures are created. Table of content, list of tables and list of figures are all created automatically from the content of the document. List of appendices is not working at this time. See item
1 | AR-10 | Character limit | Is 10 000 currently, need much more for large sections such as introduction. | JAR/PG | yes | Increased the limit to 100000 characters
2 | AR-11 | Formating | Why is the text not being inputed at the start of the page (always a 'return' too many at the top of each page). Could look at standardizing margins by default. | JAR/PG | yes | ¦¦¦PAGE_BREAK¦¦¦ should always be by itself on one line
3 | AR-12 | Question | What are the last lines at the end…seems like the same thing repeated a couple of times. Do we need this? | JAR/PG | yes | removed --- was only used for debugging purpose
1 | AR-13 | Report creating lag | Report not being created (stuck at 15%) for Baie de Tracadie | JAR/PG | yes | debugged --- pol source site which had no information was causing an error
2 | AR-14 | Table and figures titles | Titles should be Arial 10.5 | JAR | yes
2 | AR-17 | Figure 1.1 | Number at the end of the title | JAR | Yes
1 | AR-23 | Table Appendix A 1.0 | Remove runs that are not part of stats. | ALL | Yes
1 | AR-28 | List of figures and tables | Numbers after each title - solution was tu put in white (same item as AR-17) | JAR/DC | Yes
2 | AR-33 | WWTP and Municipalities | Should figures and sections be deleted automaticly if there are no WWTP or left as 'N/A'? | DC | Yes, USFDA | See also CL comments. AR-50. Will keep section and say NA or refer to other report.
| AR-43 | Section 8.2.5 | Do we still want to refer to a paper map | PG | N/A | Group decision to not reference paper maps anymore.
| AR-44 | Section 10 | Do we want to have a years specific table to insert names so this will reflect real poeple not just a generic text. Alternatively could fill out manually. | PG | Resolved | Group discussion, will type in manually.
2 | AR-32 | Space between section 2 and 3 | Should we have page breaks between sections or have them follow each other with just a return? | DC | Yes | Will keep page breaks
1 | AR-30 | Section 1.0 | Should 'Yes' and 'The revised classification is shown in Figure 8.2.0' be highligted in yellow? | DC/GP (group discussion needed) | N/A | Discussed and determined no highlight necessary.
2 | AR-45 | Section 11 | Do we want to add 'previous ECCC report' here. It does not appear in 1,0 so there are currently no mention of the previous report. | All | yes | Will be adding previous report in seciton 1.0. Should now be referenced here as well. Will type in Manually. Julie to put this section as none static in case someone wants to use webtools. | Julie : Added in section 1.0 and modified seciton 11.0.
2 | AR-48 | Datum | Add text to specify datum or coordinates in section 8.0 | PG | yes | Julie will add generic text at end of section 8.0 : All Coordinates are in Lat's and longs UGS 84 unless specified otherwise. Will also add link to Shelli. | Julie: Done
2 | AR-52 | Coordinates | Lats and long or NAD 83, do we keep old ones | CL | yes | As suggested by Dave M. Reference Shelli | Julie : Done in section 3 and 8
2 | AR-60 | Section 1.0 | To add 'previous report' as is was with other reports. | Group |  | Julie will do this. Will have to type manually previous report ID. | Julie: Done
2 | AR-61 | Section 3.0 | Group discussed the need to detail the current classification UTM/Lat and Long. Would like to just reference the Shelli link. Could still write custom text to enumerate how many closures and what type and also reference current classification map | Group |  | Julie will do this. See also AR-52 | Julie: Done in section 3 and 8

## NB Icing on the cake
Have a calendar that keeps track of the runs conpleted, managers can keep track of status of contrators
Ability to show map when accepting a FC form in the sail plan, so you can check high couts directly on the map.
Push out notification, ability to add a few custom messages i.e. st -simon 35mm please sample for MST
Rain priority list that is approved by managers prior to field season and communicated through the sampling plan